## Pivot
Sum of No. Days | Column Labels
Project Implementation Plan | Done | Grand Total
1.1. Project Purpose freezing | 2 | 2
1.2. Team Formation | 6 | 6
1.4. Colaboration channel setup (WhatsApp group) | 3 | 3
1.5. MS One Drive and Google Drive setup | 1 | 1
2.1. Literature Research | 6 | 6
2.3. Project Scoping | 3 | 3
2.4. Abstract Draft | 4 | 4
2.5. Abstract Submission | 1 | 1
3.1. Setup the Development and Testing Environment Locally for DQN | 2 | 2
3.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | 3 | 3
3.1.2. Install the Open AI Gym and all dependencies | 2 | 2
3.2. Identify the Target Label in the Open AI Gym environment (StockTradingENV: GOOGL) for DQN | 2 | 2
4.1. Setup the Development and Testing Environment Locally fro Actor Critic | 2 | 2
4.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | 3 | 3
4.1.2. Install the Open AI Gym and all dependencies | 2 | 2
4.2. Identify the Target Label in the environment (StockTradingENV: GOOGL) for Actor Critic | 2 | 2
5.1. Setup the Development and Testing Environment Locally for TRPO | 2 | 2
5.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | 3 | 3
5.1.2. Install the Open AI Gym and all dependencies | 2 | 2
5.2. Identify the Target Label in the environment (StockTradingENV: GOOGL) for TRPO | 2 | 2
6.1. Setup the Development and Testing Environment Locally for PPO | 2 | 2
6.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | 3 | 3
6.1.2. Install the Open AI Gym and all dependencies | 2 | 2
Grand Total | 60 | 60

## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Stock Prediction | [6 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | San Jose State University | [6 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | GMV Project Team |  | Project Start Date: |  | 2020-10-24
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  |  | FALSE | [6 empty] | October | [6 empty] | November | [27 empty] | December
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-10-24 to 2020-12-18
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Threat Category | Assigned To | Progress | Start | No. Days | Status |  | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | 1. Handshake and Collaboration Setup |  |  | 99% | 2020-10-24
| 1.1. Project Purpose freezing | Milestone | Team | 100% | 2020-10-30 | 2 | Done | bar: F to S
| 1.2. Team Formation | On Track | Gulnara Timokhina | 100% | 2020-10-24 | 6 | Done
| 1.3. Trello Board for Task management | Med Risk | Varun Bhaseen | 95% | 2020-10-27 | 2 | Doing
| 1.4. Colaboration channel setup (WhatsApp group) | High Risk | Poornapragna Vadiraj | 100% | 2020-10-27 | 3 | Done
| 1.5. MS One Drive and Google Drive setup | Low Risk | Mirsaeid Abolghasemi | 100% | 2020-11-02 | 1 | Done
| 2. Project Kick-off |  |  | 98% | 2020-10-27
| 2.1. Literature Research | On Track | Mirsaeid Abolghasemi | 100% | 2020-11-05 | 6 | Done
| 2.2. Problem Identification | High Risk | Gulnara Timokhina | 90% | 2020-11-01 | 4 | Doing
| 2.3. Project Scoping | Low Risk | Poornapragna Vadiraj | 100% | 2020-11-02 | 3 | Done
| 2.4. Abstract Draft | Med Risk | Varun Bhaseen | 100% | 2020-10-27 | 4 | Done
| 2.5. Abstract Submission | Milestone | Team | 100% | 2020-10-30 | 1 | Done | bar: F
| 3. DQN Baseline for Stock Prediction |  |  | 60% | 2020-11-05
| 3.1. Setup the Development and Testing Environment Locally for DQN | High Risk | Mirsaeid Abolghasemi | 100% | 2020-11-07 | 2 | Done
| 3.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | Med Risk | Mirsaeid Abolghasemi | 100% | 2020-11-05 | 3 | Done
| 3.1.2. Install the Open AI Gym and all dependencies | High Risk | Mirsaeid Abolghasemi | 100% | 2020-11-07 | 2 | Done
| 3.2. Identify the Target Label in the Open AI Gym environment (StockTradingENV: GOOGL) for DQN | Low Risk | Mirsaeid Abolghasemi | 100% | 2020-11-12 | 2 | Done
| 3.3. Setup and Train agent using DQN on the Environment | Low Risk | Mirsaeid Abolghasemi | 10% | 2020-11-13 | 5 | Doing
| 3.4. Hyperparameter Tuning for different parameters of DQN | Low Risk | Mirsaeid Abolghasemi | 0% | 2020-11-14 | 5 | Backlog
| 3.5. Record DQN results in Tensorboardx and publish link to teammates with logs | On Track | Mirsaeid Abolghasemi | 10% | 2020-11-13 | 7 | Doing
| 4. Using Actor-Critic for Stock Prediction |  |  | 58.57% | 2020-11-07
| 4.1. Setup the Development and Testing Environment Locally fro Actor Critic | High Risk | Poornapragna Vadiraj | 100% | 2020-11-07 | 2 | Done
| 4.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | Med Risk | Poornapragna Vadiraj | 100% | 2020-11-15 | 3 | Done
| 4.1.2. Install the Open AI Gym and all dependencies | High Risk | Poornapragna Vadiraj | 100% | 2020-11-13 | 2 | Done
| 4.2. Identify the Target Label in the environment (StockTradingENV: GOOGL) for Actor Critic | Low Risk | Poornapragna Vadiraj | 100% | 2020-11-15 | 2 | Done
| 4.3. Setup and Train agent on the Environment using Actor-Critic | Low Risk | Poornapragna Vadiraj | 5% | 2020-11-20 | 5 | Doing
| 4.4. Hyperparameter Tuning for different parameters of Actor Critic | Low Risk | Poornapragna Vadiraj | 0% | 2020-11-21 | 5 | Backlog
| 4.5. Record results of Actor Critic in Tensorboardx and publish link to teammates with logs | On Track | Poornapragna Vadiraj | 5% | 2020-11-22 | 7 | Doing
| 5. Using TRPO (Trust Region Policy Optimization) for Stock Prediction |  |  | 57.14% | 2020-11-21
| 5.1. Setup the Development and Testing Environment Locally for TRPO | High Risk | Gulnara Timokhina | 100% | 2020-11-07 | 2 | Done
| 5.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | Med Risk | Gulnara Timokhina | 100% | 2020-11-15 | 3 | Done
| 5.1.2. Install the Open AI Gym and all dependencies | High Risk | Gulnara Timokhina | 100% | 2020-11-13 | 2 | Done
| 5.2. Identify the Target Label in the environment (StockTradingENV: GOOGL) for TRPO | Low Risk | Gulnara Timokhina | 100% | 2020-11-15 | 2 | Done
| 5.3. Setup and Train agent on the Environment using TRPO | Low Risk | Gulnara Timokhina | 0% | 2020-11-20 | 5 | Backlog
| 5.4. Hyperparameter Tuning for different parameters of TRPO | Low Risk | Gulnara Timokhina | 0% | 2020-11-21 | 5 | Backlog
This is an empty row | 5.5. Record results of TRPO in Tensorboardx and publish link to teammates with logs | On Track | Gulnara Timokhina | 0% | 2020-11-22 | 7 | Backlog
| 6. Using PPO (Proximal Policy Optimization) for Stock Prediction |  |  | 55.71%
| 6.1. Setup the Development and Testing Environment Locally for PPO | High Risk | Varun Bhaseen | 100% | 2020-11-07 | 2 | Done
| 6.1.1. Setup Anaconda environment with all required libraries for Deep Learning (PyTorch, Tensorboard) | Med Risk | Varun Bhaseen | 100% | 2020-11-15 | 3 | Done
| 6.1.2. Install the Open AI Gym and all dependencies | High Risk | Varun Bhaseen | 100% | 2020-11-13 | 2 | Done
| 6.2. Identify the Target Label in the environment (StockTradingENV: GOOGL) for PPO | Low Risk | Varun Bhaseen | 90% | 2020-11-15 | 2 | Doing
| 6.3. Setup and Train agent on the Environment using PPO | Low Risk | Varun Bhaseen | 0% | 2020-11-20 | 5 | Backlog
| 6.4. Hyperparameter Tuning for different parameters of PPO | Low Risk | Varun Bhaseen | 0% | 2020-11-21 | 5 | Backlog
| 6.5. Record results of PPO in Tensorboardx and publish link to teammates with logs | On Track | Varun Bhaseen | 0% | 2020-11-22 | 7 | Backlog
7. Performance Comparision of Agents
| 7.1. Compare the accuracy of each technique for the trained agents | On Track | Team | 0% | 2020-11-27 | 2 | Backlog
| 7.2. Time to convergence to most optimal prediction by each agent for each technique | On Track | Team | 0% | 2020-12-02 | 5 | Backlog
| 7.3. Performance Evaluation for each Hypertuning instance for all agents | On Track | Team | 0% | 2020-12-02 | 6 | Backlog
| 7.4. Develop and publish interactive visualization for each results and draw conculsions | High Risk | Team | 0% | 2020-12-07 | 2 | Backlog
| 8. Project presentation and closure | Goal | Team | 0% | 2020-12-07 | 2 | Backlog |  | M: 2; T: 2
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one.
To add more data, Insert new rows ABOVE this one